## Sheet1
Longboat Key
Village Drainage Improvements
Project Balance Sheet
|  |  | Date: | 2003-11-04
Project Description |  | Add | Deduct | Balance
CO#1 36" Check Valve |  | 18835
Caim #1 Valve Mounting Plates (3@ $760) |  | 2280
Topsoil reduction (428 sy @ $3.50) |  |  | 1498
1 X Bar Cross Supports (@ $2,410 each) |  |  | 2410
2 X Bar Supports top only @ $800 ea. |  |  | 1600
T&M 6/16/03 8" watermain |  | 314 |  |  | 9842.1 | check against contractor balance
T&M 6/20/03 Move Sewer Serv. |  | 913.38 |  |  |  | lines 11 to 23
T&M 6/23/03 install sewer |  | 135.91
T&M 6/24/03 sewer tie-in |  | 629.26
T&M 6/24/03 cut in S-3 |  | 190
T&M 6/25/03 sewer tap |  | 824.59
T&M 6/26/03 Set and reset S-3 | * | 1642 |  |  | -210
T&M 6/27/03 Finish S-3 | * | 594 |  |  | -70
T&M 7/02/03 new 6" sewer lead |  | 1102.17
T&M 7/03/03 repair unmarked sewer |  | 214.78
T&M 7/7+10/03 Modify S-1 |  | 351 | 351
T&M 8/14/03 Excavation |  | 929
T&M 8/15/03 Modify S-15 |  | 2002.01 | 1001
Sewer Serv. Connections (line item 42) |  |  | 1230
Utility Fund Reimbursement ** |  |  | 4139.09
Proposal #1 install 3-18" valves |  | 3220.38
Proposal # 2 replace 3 structure lids with grates |  | 9576 | 9576
|  | 43753.48 | 21805.09 | 21948.39
* denotes adjusted price
** Utility Refund as separate PO for a total of $4490