## Project Budget
Project Budget
Village Drainage Study Update and Plan | [10 empty] | Town of Longboat Key
| Personnel Hours | [10 empty] | Status |  |  | Schedule
Task Description | Principal | Snr. Eng. II | Ast. Eng. II | Snr. Tech. | CADD | Clerical | Survey Crew | Total Hours | Labor | Non-Labor | Total | Percent Complete | Labor Earned to Date | Non-Labor Earned to Date | Start Date | End Date
PHASE 1 | [7 empty] | 0 | 0 |  | 0 |  | 0 | 0
Task 1 - Peer Review of Drainage Study
1.1 Data Collection and Interveiws with Town Staff |  |  | 4 | 4 |  | 2 |  | 10 | 652 | 32 | 684 |  | 0 | 0 | 2000-05-25 | 2000-06-01
1.2 Review of Drainage Study |  | 1 | 2 |  |  |  |  | 3 | 250 | 8 | 258 |  | 0 | 0 | 2000-05-25 | 2000-06-01
1.3 Review of Art Center Site Plan |  | 1 | 2 |  |  |  |  | 3 | 250 | 8 | 258 |  | 0 | 0 | 2000-05-25 | 2000-06-01
1.4 Limited survey to establish aerial targets |  |  |  |  | 8 |  | 24 | 32 | 3184 | 500 | 3684 |  | 0 | 0 | 2000-06-01 | 2000-06-08
1.5 Obtain Aerial Topographic Mapping |  | 4 | [5 empty] | 4 | 480 | 5000 | 5480 |  | 0 | 0 | 2000-06-08 | 2000-07-08
1.6 Limited additional survey of storm sewer system |  |  |  | 4 | 8 |  | 16 | 28 | 2564 | 250 | 2814 |  | 0 | 0 | 2000-07-08 | 2000-07-15
1.7 Prepare prelim. hydraulic/hydrologic model of existing storm system |  | 16 | 40 | 8 |  |  |  | 64 | 5120 | 2400 | 7520 |  | 0 | 0 | 2000-07-15 | 2000-08-01
1.8 Identify New Alternatives for Drainage Improvements (3 total) |  | 8 | 32 |  |  |  |  | 40 | 3040 | 128 | 3168 |  | 0 | 0 | 2000-08-01 | 2000-08-15
1.9 Evaluate Newly Developed Areas for Drainage Improvements |  | 4 | 12 |  |  |  |  | 16 | 1260 | 48 | 1308 |  | 0 | 0 | 2000-08-01 | 2000-08-15
1.10 Prepare Draft Update to Study (6 copies) | 2 | 8 | 16 |  | 8 | 8 |  | 42 | 3092 | 279 | 3371 |  | 0 | 0 | 2000-08-15 | 2000-09-01
1.11 Meeting with Town Staff |  | 2 | 2 |  | 8 | 1 |  | 13 | 840 | 152 | 992 |  | 0 | 0 | 2000-09-01 | 2000-09-01
Subtotal | 2 | 44 | 110 | 16 | 32 | 11 | 40 | 255 | 20732 | 8805 | 29537 | 0% | 0 | 0
Task 2 - Finalize Drainage Study Update
2.1 Identify Grant Funding Sources for Updated Study | 1 | 4 | 16 | 8 |  | 4 |  | 33 | 2454 | 96 | 2550 |  | 0 | 0 | 2000-09-01 | 2000-09-15
2.2 Coordinate Update with NFIP, CRS and FMP |  | 2 | 8 | 8 |  | 2 |  | 20 | 1452 | 48 | 1500 |  | 0 | 0 | 2000-09-01 | 2000-09-15
2.3 Coordinate Update with Database of Facilities for Future GIS |  | 1 | 4 | 4 |  | 2 |  | 11 | 772 | 32 | 804 |  | 0 | 0 | 2000-09-01 | 2000-09-15
2.4 Develop Detailed Model of Selected Alternative |  | 20 | 40 | 12 | 8 |  |  | 80 | 6324 | 296 | 6620 |  | 0 | 0 | 2000-09-01 | 2000-09-15
2.5 Prepare Final Update to Study (6 copies) | 2 | 4 | 8 |  |  | 8 |  | 22 | 1668 | 114 | 1782 |  | 0 | 0 | 2000-09-15 | 2000-09-22
2.6 Presentations to Town Departments (3 total) |  | 6 |  |  | 8 | 4 |  | 18 | 1328 | 168 | 1496 |  | 0 | 0 | 2000-09-22 | 2000-10-01
2.7 Pre-application meeting with SWFWMD |  | 2 | 2 |  |  | 1 |  | 5 | 416 | 37 | 453 |  | 0 | 0 | 2000-10-01 | 2000-10-01
Subtotal | 3 | 39 | 78 | 32 | 16 | 21 | 0 | 189 | 14414 | 791 | 15205 | 0% | 0 | 0
PHASE 2
Task 3 - Develop Bid Documents
3.1 Prepare 50% Plans from Selected Alternative (6 sets) |  | 20 | 40 | 32 | 48 | 4 |  | 144 | 10128 | 1068 | 11196 |  | 0 | 0 | 2000-10-01 | 2000-11-01
3.2 Design of stormwater BMP's ADD |  | 4 | 16 |  | 12 |  |  | 32 | 2156 | 328 | 2484 |  | 0 | 0
3.3 Environmental field work & permit asst ADD |  | 8 | 4 |  | 12 |  |  | 24 | 1856 | 405 | 2261 |  | 0 | 0
3.4 Prepare 90% Plans and Specificiations (6 sets) |  | 16 | 20 | 24 | 32 | 16 |  | 108 | 7452 | 932 | 8384 |  | 0 | 0 | 2000-11-01 | 2000-12-01
3.5 Prepare 90% Estimate of Probable Construction Cost |  | 1 | 2 | 8 |  |  |  | 11 | 850 | 25 | 875 |  | 0 | 0 | 2000-11-01 | 2000-12-01
3.6 Quality Control Review | 8 |  |  |  |  | 2 |  | 10 | 1292 | 25 | 1317 |  | 0 | 0 | 2000-12-01 | 2000-12-08
3.7 Prepare Permit Applications (FDEP/EPA, SWFWMD - 6 sets each) |  | 4 | 16 | 4 | 8 | 8 |  | 40 | 2612 | 402 | 3014 |  | 0 | 0 | 2000-11-01 | 2000-12-01
3.8 Prepare Final Bid Documents (2 sealed sets) | 1 | 4 | 4 | 16 | 8 | 8 |  | 41 | 2882 | 236 | 3118 |  | 0 | 0 | 2001-01-01 | 2001-01-15
Subtotal | 9 | 57 | 102 | 84 | 120 | 38 | 0 | 410 | 29228 | 3421 | 32649 | 0% | 0 | 0
Task 4 - Bid and Construction Phase Services
4.1 Distribute Bid Documents (15 sets) |  | 1 |  |  |  | 8 |  | 9 | 488 | 514 | 1002 |  | 0 | 0 | 2001-01-15 | 2001-02-01
4.2 Record Bidders | [5 empty] | 4 |  | 4 | 184 | 32 | 216 |  | 0 | 0 | 2001-02-01 | 2001-03-01
4.3 Respond to Questions from Bidders |  | 2 | 2 |  |  | 1 |  | 5 | 416 | 16 | 432 |  | 0 | 0 | 2001-02-01 | 2001-03-01
4.4 Prepare Addenda (3 total) |  | 3 | 3 |  |  | 3 |  | 9 | 693 | 36 | 729 |  | 0 | 0 | 2001-02-01 | 2001-03-01
4.5 Review Shop Drawings |  | 6 |  | 12 |  | 4 |  | 22 | 1804 | 32 | 1836 |  | 0 | 0 | 2001-03-01 | 2001-03-15
4.6 Construction observation/ periodic site visits |  | 3 |  | 6 |  | 2 |  | 11 | 902 | 16 | 918 |  | 0 | 0 | 2001-03-01 | 2001-06-01
4.7 Record Drawings |  | 1 | 3 |  | 8 |  |  | 12 | 739 | 148 | 887 |  | 0 | 0 | 2001-06-01 | 2001-06-15
4.8 Construction Certification (4 sets) |  | 1 | 1 |  |  | 1 |  | 3 | 231 | 52 | 283 |  | 0 | 0 | 2001-06-15 | 2001-06-15
Subtotal | 0 | 17 | 9 | 18 | 8 | 23 | 0 | 75 | 5457 | 846 | 6303 | 0% | 0 | 0
Subconsultants
Survey and R/W Mapping | [7 empty] | 0 | 0 | 4550 | 4550 |  | 0 | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4550 | 4550 | 0% | 0 | 0
Total | 14 | 157 | 299 | 150 | 176 | 93 | 40 | 929 | 69831 | 18413 | 88244 | 0% | 0 | 0
Total | 9 | 74 | 111 | 102 | 128 | 61 | 0 | 485 | 34685 | 8817 | 43502
Status Summary
Notes: The above tasks are based on the following assumptions: | [8 empty] | Personnel Category | $/HR |  | Amount Earned to Date (BCWP) |  |  | 0
1. Preparation of plans and specifications does not include specialized | [8 empty] | Principal | 150 |  | Actual Amount Spent to Date (ACWP) |  |  | 0 | As of
design services such as controls, electrical and structural. | [8 empty] | Snr. Eng. II | 120 |  | Projected Amount at Completion |  |  | 0
2. Plan set is assumed not to exceed a total of 10 sheets | [8 empty] | Ast. Eng. II | 65 |  | Projected Under/(Over) Budget |  |  | 0
3. Town will provide geotechnical services as needed. | [8 empty] | Snr. Tech. | 75
4. It is assumed that Town will pay all permit application fees. | [8 empty] | CADD | 53 |  | Budgeted Cost of Work Scheduled (BCWS) |  |  |  | As of
5. Assitance with Public Meetings is not included at this time. | [8 empty] | Clerical | 46
6. Existing utilities will be located from plans provided by the Town | [8 empty] | Survey Crew | 115 |  | Cost Variance (BCWP-ACWP) |  |  | 0
and utility owners. Subsurface location and relocation design are | [11 empty] | Schedule Variance (BCWP - BCWS) |  |  | 0
not included in this proposal.
Cost Variance %
Schedule Variance %
[12 empty] | Weeks Ahead/(Behind) Schedule |  |  |  | As of

## StatusData
Configured? | TRUE |  | Status Last Row | 11
StartDate |  | 88244 | TCR Last Row | 59
EndDate |  | 88244 | TCR Last Column | 17
CurrentODC
CurrentLabor |  |  | Version Number | 1.27
CurrentDate |  |  | Upgradeable From Version | 1
Percent Complete
Actual Costs
Status Date | Labor | ODC | Total | Earned
| 0 | 0 | 0 | 0

## ConfigData
Project name | Village Drainage Study Update and Plan
Other Project ID 1
Other Project ID 2
Client Info 1 | Town of Longboat Key
Client Info 2
Client Info 3
Number of personnel categories | 7
Number of subtotals | 5
Category Name | Rate
Principal | 150
Snr. Eng. II | 120
Ast. Eng. II | 65
Snr. Tech. | 75
CADD | 53
Clerical | 46
Survey Crew | 115
Basis for Hourly Rate | March 2001 Standard Hourly Rate Schedule
Type of Report | 1
Raw or Fee based costs | 0