## Sheet1
Town of Longboat Key - Long-term Issues 2023 - 2027
Issue | 2023 | 2024 | 2025 | 2026 | 2027
Beach Management | Construct New Pass Structure tightening near Fall 2023. | Conduct interim nourishment end of calendar 2024/beginning of 2025. Begin Comprehensive Beach Management Plan Update; consider inclusion of structural solution to Gulfside Rd area. | Update and Adopt Beach Management Plan. | Begin planning for next renourishment (FY29) | Begin survey, design and permitting next beach nourishment. Plan/budget for referendum amount.
Sea Level Rise - Comprehensive Adaptation Plan | Consultant help pursue/explore external funding options for implementation, as needed. Continue to program grant matching funds into CIP and pursue grants. Procure Norton Street road elevation design. Re-assess Village area. | Design Norton Street road elevation improvement project. Continue pursuing grant funding for design and implementation of road elevation projects. | Continue pursuing grant funding for implementation of road elevation projects. Depending on funds acquired, begin construction and continue design in Sleepy Lagoon, Buttonwood, and the Village areas. | Continue pursuing grant funding for implementation of road elevation projects. Depending on funds acquired, begin construction and continue design in Sleepy Lagoon, Buttonwood, and the Village areas. | Re-baseline and compare original projections to current. Town consider additional local funding depending on results of grant efforts.
Subaqueous Force Main | Continue to pursue outside funding opportunities. Complete mainland lining project. Complete pipeline assessment. Final assessment of feasibility of mutliple construction methods for sub-aqueous portion under Sarasota Bay. | Final Design & Permitting; additional Easement Acquisition, as needed. | Construction/CEI | Depending on cost savings or remaining budget dolars from larger project, Town consider re-lining the existing sub-aqueous pipeline portion under Sarasota Bay as a redundant force main. | Reline existing sub-aqueous force main under bay, pending available funds.
GMD Complete Streets | CCS Turn Lane: work with FDOT on Joint Project Agreement. Complete design of Broadway Roundabout.Pursue more immediate funding for Complete Streets multi-purpose trail replacement. | Identify additional funding source for Broadway Roundabout beyond $1.685 million committed by FDOT. FDOT/ Town construct CCS Turn Lane improvement. Pursue more immediate funding for Complete Streets multi-purpose trail replacement. FDOT complete two PHB's, enhanced RRFB project and mid-block crosswalk lighting project. | Pursue FDOT and MPO long-range funding for additional Complete Streets Design elements. | Continue pursuing long-term funding of GMD Complete Streets Corridor Plan projects in partnership with FDOT and MPO. See MPO Long Range Transportation Plan (“LRTP”) year 2030: Broadway Roundabout, Longboat Club Road Roundabout, full multi-purpose trail widening and replacement. Long-range funding for other complete streets elements.
Canal Dredging | Begin developing special assessment program and draft assessment resolutions. Meet with the public. | Finalize assessment resolutons and begin collecting assessments. Hire outside program /assessment manager to help organize inital program and collections. Prioritize first year area, and begin design and update permits as needed. | 1st Year Assessments complete; finalize design/permitting and begin first year of three-year Geographic Area Navigational Dredge program. | 2nd Year Assessments complete; design/permit then initiate dredge second year of three- year Geographic Area Navigational Dredge program. | 3rd Year Assessments complete; design/permit third year dredge and continue with maintenance dredging.
Town Center Phase 3 | Town work with Sarasota County on Library planning and funding for south parcel. Town determines how to handle funding for "upgrades," such as 3,000-sf multi-purpose flex space, adult learning classrooms, and upper deck space. Sarasota County function as facility operator. | Hold community charrettes and complete design of library with upgrades including Town involvement. Ensure design re-evaluates parking availability. Town and County develop operator agreement and work on construction funding. | Pending Sarasota County, Town and donor funding, construct Phase 3 | Pending Sarasota County, Town and donor funding, construct Phase 3 | Evaluate options for the North Parcel.
| Sarasota County hire design architect. | LBK Foundation begin donor efforts for construction elements as necessary.
Community Space for Adult Education on North end of Island | Continue discussions with Manatee County for services and location at Whitney Plaza.
Barrier Island Traffic Recommendations | Coordinate with FDOT on evaluation of U.S. 41 @ Gulfstream Roundabout effectiveness. Depending on effectiveness, advocate for John Ringling Counter-Flow and/or other solutions. | Continue to advocate for and pursue improvements to peak season congestion. Evaluate opportunities for water taxis/ferries to and from the island including potential landing sites. |  | Continue to advocate for and pursue improvements to peak season congestion. FDOT bridge planning/ design/ construction as applicable.
Smart City Opportunities | Implement a pilot of Smart City solutions (iOT) that add value to the Town and enhance self-service to the community (FY23/24) | Evaluate current system and determine other possible options to add | Technology adjustments based on current conditions.
Rec Center- Bayfront Park |  | If existing structure still in service- replace existing rec center roof FY 24. Town Center Phase 3 plan for fitness class space…(?) | Initiate concept planning for the ultimate replacement of the Rec Center - potentially with a 2-story open air structure that can provide storage, parking and other space underneath for the Town while still facilitating outdoor activities at the Park |  | Upon construction completion Town Center Phase 3, plan for future repurposing of Bayfront Park rec center location.
Evaluation of Commercial and Tourism balance |  | Start an analysis/study of issues including Commercial/Jobs/Tourism Housing Balance | Consider Comprehensive Plan/Town Code Updates/Revisions
Water System Augmentation and Reclaim Water on the Island | Explore modifications to City of Sarasota Interconnect agreement for high-usage seasons. Evaluate other engineering options to augment system. | Conduct feasibility study for island reclaim water to serve irrigation. Feasibility to include reclaim source, infrastructure requirements, and planning level costs.
Gulf of Mexico Drive Lighting: New Lit Street Name Signs, additional roadway lighting, and Mutlit-Use Trail Lighting | Review options and costs for new lit street name signs Town wide. Select an option to implement in FY 2024. | Implement new lit street name signs. In addition, assess GMD lighting after Underground Project is complete and lit street name signs installed. Develop options for additonal roadway and pathway lighting. Work with Town Manager and Town Commisison.